## Product Backlog
Project Name | Amazon
Client | Amazon
Created By | Shivam Patel
Creation Date | 26/4/2024
Approval Date | 2024-06-05
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Creteria
| US -02 | Check the global search dropdown should get auto selected when clicked on: ● Electronics ● Mobile ● Fashions ● Home and kitchen ● Books ● Computers ● By default it should be all even if we click on other option of the menu or invalid search in that category | Check the global search dropdown should get auto selected when clicked on : ● Electronics ● Mobile ● Fashions ● Home and kitchen ● Books ● Computers ● By default it should be all even if we click on other option of the menu or invalid search in that category | Done | 1. By default value of the dropdown should be All. 2. User select any of the listed value then the global search dropdown value should change Automatically. 3. If the user select electronic and search for shirt it should default to all because of invalid category

## Sprint Planning
Project Name | Amazon
Client | Amazon
Created By | Shivam Patel
Attendees | Shivam Patel
Creation Date | 2024-04-26
Epic | User Story ID | Feature/Title | User Story | Sprint
Epic 1 | US -02 | Check the global search dropdown should get auto selected when clicked on ● Electronics ● Mobile ● Fashions ● Home and kitchen ● Books ● Computers ● By default it should be all even if we click on other option of the menu or invalid search in that category | Check the global search dropdown should get auto selected when clicked on ● Electronics ● Mobile ● Fashions ● Home and kitchen ● Books ● Computers ● By default it should be all even if we click on other option of the menu or invalid search in that category | 1
Story Points | Hours
1 | 1 Day
0,1, 1, 2, 3, 5, 8 | Fibinacci series

## Test scenarios
Project- Amazon Application E-commerce
Project Name | Amazon
Module Name | Amazon
Requirement Number | NA
Test case Type | Functionality testing
Reference Doccument | NA
Pre-condition
Test Data
Test Data
Test Senario number | Description
TS-001 | To check by default value of the dropdown should be All.
TS-002 | To check User selects from the listed value then the global search dropdown value should change Automatically
TS-003 | To check invalid category when the user selects from listed options and search for specific items, defaulted to ALL

## Test cases
Test case number | Test case name | Description | Test Steps | Test Data | Expected Result | Actual Result | Severity | Priority | Tested By | Test Status | Test Creation Date | Test Execution Date
TC_01 | Default value of dropdown | To check by default value of the dropdown should be All. | Go to URL available at: https://www.amazon.in/ |  | Default value of the dropdown should be All. | Default value of the dropdown is All. | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_02 | select "Electronics" of the listed value then the global search dropdown value should change Automatically to "Electronics" | To check User select "Electronics" of the listed value then the global search dropdown value should change Automatically to "Electronics" | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Electronics" Tab 3. User clicks on "Electronics" Tab |  | 3. Global search dropdown value should change automatically to "Electronics" from default All | 3. Global search dropdown value is change automatically to "Electronics" from default All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_03 | select "Mobile" of the listed value then the global search dropdown value should change Automatically to "Mobile" | To check User select "Mobile" of the listed value then the global search dropdown value should change Automatically to "Mobile" | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Mobile" Tab 3. User clicks on "Mobile" Tab |  | 3. Global search dropdown value should change automatically to "Mobile" from default All | 3. Global search dropdown value is change automatically to "Mobile" from default All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_04 | select "Fashions" of the listed value then the global search dropdown value should change Automatically to "Fashions" | To check User select "Fashions" of the listed value then the global search dropdown value should change Automatically to "Fashions" | 1. Go to URL available at: https://www.amazon.in/ 2 User hovers over "Fashions" Tab 3. User clicks on "Fashions" Tab |  | 3. Global search dropdown value should change automatically to "Fashions" from default All | 3. Global search dropdown value is change automatically to "Fashions" from default All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_05 | select "Home & Kitchen" of the listed value then the global search dropdown value should change Automatically to "Home & Kitchen" | To check User select "Home & Kitchen" of the listed value then the global search dropdown value should change Automatically to "Home & Kitchen" | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Home & Kitchen" Tab 3. User clicks on "Home & Kitchen" Tab |  | 3. Global search dropdown value should change automatically to "Home & Kitchen" from default All | 3. Global search dropdown value is change automatically to "Home & Kitchen" from default All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_06 | select "Books " of the listed value then the global search dropdown value should change Automatically to "Books" | To check User select "Books " of the listed value then the global search dropdown value should change Automatically to "Books" | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Books" Tab 3. User clicks on "Books" Tab |  | 3. Global search dropdown value should change automatically to "Books" from default All | 3. Global search dropdown value is change automatically to "Books" from default All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_07 | select "Computers" of the listed value then the global search dropdown value should change Automatically to "Computers" | To check User select "Computers" of the listed value then the global search dropdown value should change Automatically to "Computers" | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Computers" Tab 3. User clicks on "Computers" Tab |  | 3. Global search dropdown value should change automatically to "Computers" from default All | 3. Global search dropdown value is change automatically to "Computers" from default All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_08 | select " Amazon miniTV" of the listed menu then the global search dropdown value should be defaulted to All | To check User select " Amazon miniTV" of the listed menu then the global search dropdown value should be defaulted to All | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Amazon miniTV" Tab 3. User clicks on "Amazon miniTV" Tab |  | 3. Global search dropdown value should change automatically to All | 3. Global search dropdown value is not changed automatically to All and is navigated to different window for "Amazon miniTV" | High | Medium | Shivam P. | Fail | 2024-04-27 | 2024-04-27
TC_09 | select " Sell" of the listed menu then the global search dropdown value should be defaulted to All | To check User select " Sell" of the listed menu then the global search dropdown value should be defaulted to All | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Sell" Tab 3. User clicks on "Sell" Tab |  | 3. Global search dropdown value should change automatically to All | 3. Global search dropdown value is change automatically to All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_10 | select " Best Sellers" of the listed menu then the global search dropdown value should be defaulted to All | To check User select " Best Sellers" of the listed menu then the global search dropdown value should be defaulted to All | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Best Sellers" Tab 3. User clicks on "Best Sellers" Tab |  | 3. Global search dropdown value should change automatically to All | 3. Global search dropdown value is change automatically to All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_11 | select " Today's Deal" of the listed menu then the global search dropdown value should be defaulted to All | To check User select " Today's Deal" of the listed menu then the global search dropdown value should be defaulted to All | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Today's Deal" Tab 3. User clicks on "Today's Deal" Tab |  | 3. Global search dropdown value should change automatically to All | 3. Global search dropdown value is change automatically to All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_12 | select " Customer Service" of the listed menu then the global search dropdown value should be defaulted to All | To check User select " Customer Service" of the listed menu then the global search dropdown value should be defaulted to All | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Customer Service" Tab 3. User clicks on "Customer Service" Tab |  | 3. Global search dropdown value should change automatically to All | 3. Global search dropdown value is change automatically to All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_13 | select "Amazon Pay" of the listed menu then the global search dropdown value should be defaulted to All | To check User select "Amazon Pay" of the listed menu then the global search dropdown value should be defaulted to All | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Amazon Pay" Tab 3. User clicks on "Amazon Pay" Tab |  | 3. Global search dropdown value should change automatically to All | 3. Global search dropdown value is change automatically to All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_14 | select "New Releases" of the listed menu then the global search dropdown value should be defaulted to All | To check User select "New Releases" of the listed menu then the global search dropdown value should be defaulted to All | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "New Releases" Tab 3. User clicks on "New Releases" Tab |  | 3. Global search dropdown value should change automatically to All | 3. Global search dropdown value is change automatically to All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_15 | User select "Prime" of the listed menu then the global search dropdown value should be defaulted to All and navigated to a different window | To check User select "Prime" of the listed menu then the global search dropdown value should be defaulted to All and navigated to a different window | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Prime" Tab 3. User clicks on "Prime" Tab |  | 3. Global search dropdown value should change automatically to All | 3. Global search dropdown value is change automatically to All | High | High | Shivam P. | Pass | 2024-04-27 | 2024-04-27
TC_16 | Invalid category when the user selects electronics and search for shirt, defaulted to ALL. | To check invalid category when the user selects electronics and search for shirt, defaulted to ALL. | 1. Go to URL available at: https://www.amazon.in/ 2. User hovers and clicks on "Electronics" 3. Enter keyword in the global search and click on search | 3. shirt | 2. Global search dropdown value should change automatically to "Electronics" from default All 3. Global dropdown should be defaulted to All | 2. Global search dropdown value is change automatically to "Electronics" from default All 3. Global dropdown is defaulted to All | Medium | Medium | Shivam P. | Pass | 2024-04-27 | 2024-04-27

## Test excution details
Test Case id | Test Case Name | Screenshots
TC_01 | Default value of dropdown
TC_02 | select "Electronics" of the listed value then the global search dropdown value should change Automatically to "Electronics"
TC_03 | select "Mobile" of the listed value then the global search dropdown value should change Automatically to "Mobile"
TC_04 | select "Fashions" of the listed value then the global search dropdown value should change Automatically to "Fashions"
TC_05 | select "Home & Kitchen" of the listed value then the global search dropdown value should change Automatically to "Home & Kitchen"
TC_06 | select "Books " of the listed value then the global search dropdown value should change Automatically to "Books"
TC_07 | select "Computers" of the listed value then the global search dropdown value should change Automatically to "Computers"
TC_08 | select " Amazon miniTV" of the listed menu then the global search dropdown value should be defaulted to All
TC_09 | select " Sell" of the listed menu then the global search dropdown value should be defaulted to All
TC_10 | select " Best Sellers" of the listed menu then the global search dropdown value should be defaulted to All
TC_11 | select " Today's Deal" of the listed menu then the global search dropdown value should be defaulted to All
TC_12 | select " Customer Service" of the listed menu then the global search dropdown value should be defaulted to All
TC_13 | select "Amazon Pay" of the listed menu then the global search dropdown value should be defaulted to All
TC_14 | select "New Releases" of the listed menu then the global search dropdown value should be defaulted to All
TC_15 | User select "Prime" of the listed menu then the global search dropdown value should be defaulted to All and navigated to a different window
TC_16 | Invalid category when the user selects electronics and search for shirt, defaulted to ALL.

## Defects
Defect number | Project Name | Module Name | Requirement Number | Test Case ID | Summary | Description | Issues | Severity | Priority | Assign to | Screen Shots
DN0123 | Amazon | Amazon | RN_01 | TC_08 | select " Amazon miniTV" of the listed menu then the global search dropdown value should be defaulted to All | Steps to reproduce: 1. Go to URL available at: https://www.amazon.in/ 2. User hovers over "Amazon miniTV" Tab 3. User clicks on "Amazon miniTV" Tab Environment: OS: Windows 11, version 22h2 Browser: Google chrome Language: English | Expected result: Global search dropdown value should change automatically to All Actual Result: Global search dropdown value is not changed automatically to All and is navigated to different window for "Amazon miniTV" | High | Medium | Shivam P.

## Defect_Snapshots
Defect Number | TC_id | Summary | Screenshots
DN0123 | TC_08 | select " Amazon miniTV" of the listed menu then the global search dropdown value should be defaulted to All

## Story_Point_Effort_and_Reason
Project Name :- | Amazon
Story Point :- | 1
Reason for story point :- | To validate Global search dropdown features
Efforts(in hours) :- | 8 HR
Reason for Efforts :- | Test case preparation - 4 hrs Test case execution - 3 hrs Raising Bugs/Retesting: 1 hr

## Test report
SNO | PASS | FAIL | BLOCKERS | NOT EXECUTED | TOTAL TEST CASE | PASS RATIO (%) | TEST IN PROGRESS | DEV IN PROGRESS | DONE | TOTAL DEFECT
US_02 | 15 | 1 | 0 | 0 | 16 | 93.75% | 0 | 0 | 16 | 1